{"text_format":"3","workbook":"xls","n_sheets":16,"sheets":["封-1_招标工程量清单","扉-1_招标工程量清单","表-01_总说明","表-02_建设项目投标报价汇总表","表-03_单项工程投标报价汇总表","表-04_单位工程投标报价汇总表","表-08_分部分项工程和单价措施项目清单与计价表","表-11_总价措施项目清单与计价表","表-12-1_暂列金额明细表","表-12-2_材料(工程设备)暂估单价表及调整表","表-12-3_专业工程暂估价及结算价表","表-12-4_计日工表","表-12-5_总承包服务费计价表","表-14_税前项目清单与计价表","表-15_规费、增值税计价表","表-22_承包人提供主要材料和工程设备一览表"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"封-1_招标工程量清单","index":0,"n_rows":12,"n_cols":5,"rows_kept":12,"merged":[[0,1,0,2],[1,1,1,3],[2,2,3,2],[5,2,6,2],[8,1,8,3],[9,1,9,3],[10,0,10,1],[10,2,10,4]],"flags":["formulas_cached_only"]}
[null,"中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护",null,"工程"]
[null,"招 标 工 程 量 清 单"]
[]
[null,"招  标  人:"]
[null,null,"(单位盖章)"]
[]
[null,"造价咨询人:"]
[null,null,"(单位盖章)"]
[null,"2019年07月03日"]
[null,"软件名称及版本号：博奥清单计价软件V17（版本号：17.0.01）\r\n工程计价软件测评合格编号：2016J02"]
[]
[{"$nulls":4},"封-1"]

{"sheet":"扉-1_招标工程量清单","index":1,"n_rows":49,"n_cols":9,"rows_kept":49,"merged":[[3,1,3,6],[7,1,7,7],[16,2,17,4],[16,6,17,8],[17,0,17,1],[18,2,18,4],[18,6,18,8],[24,0,24,1],[24,2,25,4],[24,6,25,8],[25,0,25,1],[26,2,26,4],[26,6,26,8],[32,2,33,4],[32,6,33,8],[33,0,33,1],[34,2,34,4],[34,6,34,8],[41,0,41,1],[41,2,41,4],[41,6,41,8],[46,2,46,7]],"flags":["formulas_cached_only"]}
[]
[]
[]
[null,"中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护",{"$nulls":5},"工程"]
[]
[]
[]
[null,"招 标 工 程 量 清 单"]
{"$rows_empty":9}
["  招  标  人:",{"$nulls":4},"造价咨询人："]
[null,null,"（单位盖章）",{"$nulls":3},"（单位资质专用章）"]
[]
[]
[]
[]
[]
["  法定代表人 ",{"$nulls":4},"法定代表人  "]
["或其授权人：",{"$nulls":4},"或其授权人："]
[null,null,"（签字或盖章）",{"$nulls":3},"（签字或盖章）"]
[]
[]
[]
[]
[]
[]
["编  制  人：",{"$nulls":4},"复  核  人："]
["                 ",null,"（造价人员签字）",{"$nulls":3},"(造价工程师签字盖专用章)"]
[]
[]
[]
[]
[]
[]
["  编 制 时 间:",null,"2019年07月03日",null,null,"复 核 时 间：","2019年07月03日"]
[]
[]
[]
[]
[]
[]
[{"$nulls":8},"扉-1"]

{"sheet":"表-01_总说明","index":2,"n_rows":38,"n_cols":3,"rows_kept":38,"merged":[[0,0,0,2],[2,0,36,2]],"flags":["formulas_cached_only"]}
["总  说  明"]
["工程名称:","中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程","第1页 共1页"]
["    一、工程概况：该项目为浆砌片石明沟及边坡防护工程。\n    二、编制范围：主要内容包括边坡防护长度约140米，浆砌片石明沟长约40米。\n    三、编制依据：\n    1、《建设工程工程量清单计价规范》(GB 50500-2013)、《房屋建筑与装饰工程工程量计算规范》(50854-2013)、《通用安装工程工程量计算规范》(50856-2013)广西壮族自治区住房和城乡建设厅颁布的《建设工程工程量清单计价规范》（GB 50500-2013）广西壮族自治区实施细则、《建设工程工程量计算规范》（GB 50854～50862-2013）广西壮族自治区实施细则》修订本；\n    2、广西壮族自治区建设行政主管部门颁发的2014年《广西壮族自治区市政工程消耗量定额》、2014年《广西壮族自治区市政工程费用定额 》、2013年《广西壮族自治区园林绿化及仿古建筑工程消耗量定额》、2013年《广西壮族自治区园林绿化及仿古建筑工程费用定额》等。\n    3、广西壮族自治区住房和城乡建设厅2018年7月2日发布的桂建标[2018]19号《关于调整建设工程定额人工费及有关费率的通知》；\n    4、《关于建筑业实施营业税改征增值税后广西壮族自治区建设工程计价依据调整的通知》（桂建标[2016]17号）、《关于颁布2016年广西壮族自治区建设工程费用定额的通知》（桂建标[2016]16号）；《自治区住房城乡建设关于调整建设工程计价增值税税率的通知》 （桂建标[2018]14号）；\n    5、材料价格参考《钦州市建设工程造价信息》2019年第5期发布的钦州港信息价计取，信息价中档次的材料价格。钦州港信息价没有的参考同期钦州市、南宁市除信息价或市场询价；\n    6、与建设工程项目有关的标准、规范、技术资料；\n    四、其他情况说明:  \n    1、本工程采用商品砼；\n    2、弃土运距按3km计算。\n"]
{"$rows_empty":34}
[null,"表-01"]

{"sheet":"表-02_建设项目投标报价汇总表","index":3,"n_rows":35,"n_cols":5,"rows_kept":35,"merged":[[0,0,0,4],[1,0,1,3],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,2,4],[3,3,4,3]],"flags":["formulas_cached_only"]}
["建设项目投标报价汇总表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":3},"第1页 共1页"]
["序号","单项工程名称","金额(元)","其中:(元)"]
[{"$nulls":3},"暂估价","安全文明"]
[{"$nulls":4},"施工费"]
[null,"        投标报价合计"]
{"$rows_empty":28}
[{"$nulls":4},"表-02"]

{"sheet":"表-03_单项工程投标报价汇总表","index":4,"n_rows":35,"n_cols":5,"rows_kept":35,"merged":[[0,0,0,4],[1,0,1,3],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,2,4],[3,3,4,3]],"flags":["formulas_cached_only"]}
["单项工程投标报价汇总表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":3},"第1页 共1页"]
["序号","单位工程名称","金额(元)","其中:(元)"]
[{"$nulls":3},"暂估价","安全文明"]
[{"$nulls":4},"施工费"]
["1.1","浆砌片石明沟及边坡防护工程"]
[null,"        投标报价合计"]
{"$rows_empty":27}
[{"$nulls":4},"表-03"]

{"sheet":"表-04_单位工程投标报价汇总表","index":5,"n_rows":42,"n_cols":4,"rows_kept":42,"merged":[[0,0,0,3],[1,0,1,2]],"flags":["formulas_cached_only"]}
["单位工程投标报价汇总表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",null,null,"第1页 共1页"]
["序号","汇总内容","金额(元)","备注"]
[null,"浆砌片石明沟及边坡防护工程"]
["1","分部分项工程和单价措施项目清单计价合计"]
[" 1.1","  其中:暂估价"]
["2","总价措施项目清单计价合计"]
[" 2.1","  其中:安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费"]
["6","增值税"]
["7","工程总造价=1+2+3+4+5+6"]
[null,"工程项目汇总"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","  其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","  其中:安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费"]
["6","增值税"]
["7","工程总造价=1+2+3+4+5+6"]
{"$rows_empty":18}
[null,null," ","表-04"]

{"sheet":"表-08_分部分项工程和单价措施项目清单与计价表","index":6,"n_rows":129,"n_cols":8,"rows_kept":129,"merged":[[0,0,0,7],[1,0,1,5],[1,6,1,7],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,3],[2,4,4,4],[2,5,2,7],[3,5,4,5],[3,6,4,6],[43,0,43,7],[44,0,44,5],[44,6,44,7],[45,0,47,0],[45,1,47,1],[45,2,47,2],[45,3,47,3],[45,4,47,4],[45,5,45,7],[46,5,47,5],[46,6,47,6],[86,0,86,7],[87,0,87,5],[87,6,87,7],[88,0,90,0],[88,1,90,1],[88,2,90,2],[88,3,90,3],[88,4,90,4],[88,5,88,7],[89,5,90,5],[89,6,90,6]],"flags":["formulas_cached_only"]}
["分部分项工程和单价措施项目清单与计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":5},"第1页 共3页"]
["序\r\n\r\n号","项目编码","项目名称及\r\n项目特征描述","计量单位","工程量","金额(元)"]
[{"$nulls":5},"综合单价","合 价","其中："]
[{"$nulls":7},"暂估价"]
[null,null,"浆砌片石明沟及边坡防护工程"]
[null,null,"分部分项工程"]
[null,null,"土石方工程"]
["1","040101001","挖明沟土方","","352.00"]
[null,null,"土壤类别:三类土"]
[null,null,"挖土深度:0.4m"]
["2","040701001","边坡整理","㎡","2240.00"]
[null,null,"部位:护坡处"]
[null,null,"坡度:45°"]
["3","040103002001","余方弃置","","1248.00"]
[null,null,"废弃料品种:开挖土方"]
[null,null,"运距:3km"]
[null,null,"道路工程"]
["4","040305003001","浆砌块料","","630.14"]
[null,null,"材料品种:片石"]
[null,null,"厚度:40cm"]
[null,null,"砂浆强度等级:M10水泥砂浆"]
["5","040303024001","C25砼预制块镶边石","","56.56"]
[null,null,"部位：骨架护坡处"]
[null,null,"混凝土强度等级:C25商品砼"]
["6","040305005001","水泥砂浆抹面","㎡","1580.95"]
[null,null,"部位：骨架护坡处"]
[null,null,"厚度：1cm"]
[null,null,"1:2水泥砂浆抹面"]
["7","050102012001","铺种草皮","㎡","1281.28"]
[null,null,"草皮种类:植草护坡"]
[null,null,"铺种方式:满铺"]
[null,null,"养护期:12个月"]
["8","050101009","种植土回(换)填","","384.38"]
["9","040201023001","盲沟","m","37.00"]
[null,null,"φ80PVC排水管"]
["10","040402017001","沉降缝","m","150.00"]
[null,null,"2cm沉降缝"]
[null,null,"内填沥青麻筋"]
["11","040305003001","明沟片石砌筑","","353.80"]
[null,null,"砌体材料:片石"]
[null,null,"砂浆强度等级:M10水泥砂浆"]
[{"$nulls":7},"表-08"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":5},"第2页 共3页"]
["序\r\n\r\n号","项目编码","项目名称及\r\n项目特征描述","计量单位","工程量","金额(元)"]
[{"$nulls":5},"综合单价","合 价","其中："]
[{"$nulls":7},"暂估价"]
[null,null,"每隔8米设置一处平台泄水口"]
["12","040305005001","水泥砂浆抹面","㎡","720.00"]
[null,null,"部位：明沟"]
[null,null,"1:2水泥砂浆抹面"]
["13","040601029001","伸缩缝","m","32.00"]
[null,null,"明沟坡面10m设置一道宽2cm的伸缩缝"]
[null,null,"内填沥青麻筋"]
[]
[]
[]
[]
[null,null,"     小    计"]
[null,null,"     ∑人工费"]
[null,null,"     ∑材料费"]
[null,null,"     ∑机械费"]
[null,null,"     ∑管理费"]
[null,null,"     ∑利  润"]
[null,null,"单价措施项目"]
[null,"041101","脚手架工程"]
["14","桂041101006001","外墙脚手架","㎡","2240.00"]
[null,null,"钢管双排 10m以内"]
[null,"041103","围堰"]
["15","桂041103003001","土石围堰","","90.00"]
[]
[]
[null,null,"     小    计"]
[null,null,"     ∑人工费"]
[null,null,"     ∑材料费"]
[null,null,"     ∑机械费"]
[null,null,"     ∑管理费"]
[null,null,"     ∑利  润"]
[null,null,"     合    计"]
[null,null,"     ∑人工费"]
[null,null,"     ∑材料费"]
[null,null,"     ∑机械费"]
[null,null,"     ∑管理费"]
[null,null,"     ∑利  润"]
[{"$nulls":7},"表-08"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":5},"第3页 共3页"]
["序\r\n\r\n号","项目编码","项目名称及\r\n项目特征描述","计量单位","工程量","金额(元)"]
[{"$nulls":5},"综合单价","合 价","其中："]
[{"$nulls":7},"暂估价"]
[null,null,"     总 合 计"]
[null,null,"     ∑人工费"]
[null,null,"     ∑材料费"]
[null,null,"     ∑机械费"]
[null,null,"     ∑管理费"]
[null,null,"     ∑利  润"]
{"$rows_empty":31}
[{"$nulls":7},"表-08"]

{"sheet":"表-11_总价措施项目清单与计价表","index":7,"n_rows":41,"n_cols":7,"rows_kept":41,"merged":[[0,0,0,6],[1,0,1,4],[5,3,8,3],[39,0,39,6]],"flags":["formulas_cached_only"]}
["总价措施项目清单与计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程   ",{"$nulls":5},"第1页 共1页"]
["序\r\n号","项目编码","项 目 名 称","计 算 基 础","费 率(%)\r\n或标准","金 额(元)","备注"]
[null,null,"浆砌片石明沟及边坡防护工程"]
["一",null,"市政综合工程(营改增)一般计税法"]
["1","桂041201001001","安全文明施工费","∑分部分项、单价措施(人工费+机械费)"]
["2","桂041201002001","检验试验配合费"]
["3","桂041201003001","雨季施工增加费"]
["4","桂041201004001","工程定位复测费"]
[null,null,"      合     计"]
{"$rows_empty":29}
["注：以项计算的总价措施，无“计算基础”和“费率”的数值，可只填“金额”数值，但应在备注栏说明施工方案出处或计算方式。"]
[{"$nulls":6},"表-11"]

{"sheet":"表-12-1_暂列金额明细表","index":8,"n_rows":41,"n_cols":5,"rows_kept":41,"merged":[[0,0,0,4],[1,0,1,3],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[39,0,39,4]],"flags":["formulas_cached_only"]}
["暂列金额明细表"]
["工程名称：中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":3},"第1页 共1页"]
["序号","项目名称","计量单位","暂定金额(元)","备注"]
[]
[null,"合       计"]
{"$rows_empty":34}
["注：此表由招标人填写，如不能详列，也可只列暂定金额总额，投标人应将上述暂列金额计入总价中。"]
[{"$nulls":4},"表－12－1"]

{"sheet":"表-12-2_材料(工程设备)暂估单价表及调整表","index":9,"n_rows":29,"n_cols":12,"rows_kept":29,"merged":[[0,0,0,11],[1,0,1,9],[1,10,1,11],[2,0,3,0],[2,1,3,1],[2,3,2,4],[2,5,2,6],[2,7,2,8],[2,9,2,10],[2,11,3,11],[26,0,26,11],[27,0,27,11]],"flags":["formulas_cached_only"]}
["材料(工程设备)暂估单价及调整表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程   ",{"$nulls":9},"第1页 共1页"]
["序号","材料名称、规格、型号","计量","数量",null,"暂估(元)",null,"确认(元)",null,"差额(元)",null,"备注"]
[null,null,"单位","暂估数量","确认数量","单价","合价","单价","合价","单价","合价"]
[1,"            合   计"]
[2,"         其中：甲供材"]
{"$rows_empty":20}
[" 注：此表由招标人填写“暂估单价”，投标人应将上述材料、工程设备暂估单价计入工程量清单综合单价报价中。如为甲供材需在备注中说明“甲供材”。"]
[" 材料、工程设备暂估价、确认价均应为除税价格，结算价格差额只计取增值税。"]
[{"$nulls":11},"表-12-2"]

{"sheet":"表-12-3_专业工程暂估价及结算价表","index":10,"n_rows":43,"n_cols":6,"rows_kept":43,"merged":[[0,0,0,5],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[40,0,40,5],[41,0,41,5]],"flags":["formulas_cached_only"]}
["专业工程暂估价及结算表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":4},"第1页 共1页"]
["序号","工  程  名  称","工程内容","暂估金额(元)","结算金额(元)","备注"]
[]
[null,"            合       计"]
{"$rows_empty":35}
["注：此表“暂估金额”由招标人填写，投标人应将“暂估金额”计入投标总价中。结算时按合同约定结算金额填写。"]
["专业工程暂估金额为不包含增值税（可抵扣进项税额）的费用。"]
[{"$nulls":5},"表－12－3"]

{"sheet":"表-12-4_计日工表","index":11,"n_rows":42,"n_cols":6,"rows_kept":42,"merged":[[0,0,0,5],[1,0,1,4],[38,0,38,5],[39,0,39,5],[40,0,40,5]],"flags":["formulas_cached_only"]}
["计 日 工 表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程  ",{"$nulls":4},"第1页 共1页"]
["编号","项  目  名  称","单位","暂定数量","综合单价(元)","合价(元)"]
[null,"            总       计"]
{"$rows_empty":34}
["注：1.此表项目名称、暂定数量由招标人填写，编制招标控制价时，单价由招标人按有关计算规定确定。   "]
["2.投标时，单价由投标人自主报价，按暂定数量计算合价计入投标总介中。"]
["3.计日工单价包含除增值税以外的所有费用。"]
[{"$nulls":5},"表-12-4"]

{"sheet":"表-12-5_总承包服务费计价表","index":12,"n_rows":43,"n_cols":6,"rows_kept":43,"merged":[[0,0,0,5],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[40,0,40,5],[41,0,41,5]],"flags":["formulas_cached_only"]}
["总承包服务费计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":4},"第1页 共1页"]
["序号","项目名称","计算基础（元）","服务内容","费率(%)","金额(元)"]
[]
[null,"       合     计"]
{"$rows_empty":35}
["注：此表项目名称、服务内容由招标人填写，编制招标控制价时，费率及金额由招标人按有关计价规定确定。"]
["投标时，费率及金额由投标人自主报价，计入投标总价中。此表项目价值在结算时，计算基础按实计取。"]
[{"$nulls":5},"表－12－5"]

{"sheet":"表-14_税前项目清单与计价表","index":13,"n_rows":43,"n_cols":7,"rows_kept":43,"merged":[[0,0,0,6],[1,0,1,5],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,3],[2,4,4,4],[2,5,2,6],[3,5,4,5],[3,6,4,6],[41,0,41,6],[42,0,42,4]],"flags":["formulas_cached_only"]}
["税前项目清单与计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":5},"第1页 共1页"]
["序号","项目编码","项目名称及项目特征\r\n描述","计量单位","工程量","金  额(元)"]
[{"$nulls":5},"单价","合 价"]
[]
[null,null,"               合             计"]
{"$rows_empty":35}
["注：税前项目包含除增值税以外的所有费用。"]
[{"$nulls":6},"表-14"]

{"sheet":"表-15_规费、增值税计价表","index":14,"n_rows":41,"n_cols":5,"rows_kept":41,"merged":[[0,0,0,4],[1,0,1,3],[6,2,13,2]],"flags":["formulas_cached_only"]}
["规费、增值税计价表"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":3},"第1页 共1页"]
["序号","项目名称","计算基础","计算费率(%)","金额(元)"]
[null,"浆砌片石明沟及边坡防护工程"]
["一","市政综合工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
["1.3","工程排污费"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"       合          计"]
{"$rows_empty":24}
[{"$nulls":4},"表-15"]

{"sheet":"表-22_承包人提供主要材料和工程设备一览表","index":15,"n_rows":31,"n_cols":10,"rows_kept":31,"merged":[[0,0,0,9],[1,0,1,9],[2,0,2,7],[2,8,2,9],[28,0,28,9],[29,0,29,9]],"flags":["formulas_cached_only"]}
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:中国—马来西亚钦州产业园区燕窝加工贸易基地项目地块虾港河河道及边坡防护工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[1,"市政人工","元",null,null,1.24]
[2,"园林绿化人工","元",null,null,{"v":1.3,"d":"1.30"}]
[3,"镀锌铁丝(综合)","kg",null,null,5.68]
[4,"普通硅酸盐水泥 32.5MPa","t",null,null,383.91]
[5,"砂(综合)","",null,null,228.02]
[6,"中砂","",null,null,228.02]
[7,"毛石(块石)","",null,null,96.51]
[8,"石油沥青 30#","kg",null,null,4.26]
[9,"PVC φ80","m",null,null,7.87]
[10,"种植土","",null,null,25.64]
[11,"水","",null,null,3.11]
[12,"回转扣件","个",null,null,{"v":5.4,"d":"5.40"}]
[13,"对接扣件","个",null,null,{"v":5.4,"d":"5.40"}]
[14,"直角扣件","个",null,null,5.49]
[15,"脚手架焊接钢管 Φ48.3×3.6","t",null,null,4164.56]
[16,"碎石 GD40  商品普通砼  C25","",null,null,{"v":393.2,"d":"393.20"}]
[17,"草皮","",null,null,6.61]
[18,"机械台班人工费","元",null,null,{"v":1.3,"d":"1.30"}]
[19,"国V汽油 92#","kg",null,null,8.42]
[20,"轻柴油 0#","kg",null,null,7.04]
[21,"电","kW.h",null,null,0.69]
[22,"            合       计"]
[]
[]
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。\r\n"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-22"]