{"text_format":"3","workbook":"xls","n_sheets":14,"sheets":["封-1_工程预算书","表-01_总说明","表-02_建设项目预算招标汇总表","表-03_单项工程预算招标汇总表","表-04_单位工程预算汇总表（分专业）","表-08_分部分项工程和单价措施项目费用表","表-09_总价措施费用表","表-10_其他项目计价表","表-12_税前项目费表","表-13_规费、税金汇总表","表-19_发包人提供主要材料和工程设备一览表","表-20_承包人提供主要材料和工程设备一览表","主要材料价格表(打勾部分)","设备及价格表"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"封-1_工程预算书","index":0,"n_rows":12,"n_cols":5,"rows_kept":12,"merged":[[0,0,0,5],[1,0,1,5],[2,0,2,5],[3,0,3,5],[4,1,4,2],[4,4,4,5],[5,1,5,2],[5,4,5,5],[6,1,6,2],[6,4,6,5],[7,1,7,2],[7,4,7,5],[8,1,8,2],[8,3,8,4],[9,1,9,2],[9,3,9,4],[11,0,11,5]],"flags":["formulas_cached_only"]}
["～～～～～～～～～～～～～～～～～～～～～～～～～～～～～～"]
["工    程    预    算    书"]
["～～～～～～～～～～～～～～～～～～～～～～～～～～～～～～"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程"]
["         建设单位:","广西中马钦州产业园区开发有限公司",null,"工程造价:"]
["         施工单位:",null,null,"建筑面积:","㎡"]
["         编制单位:",null,null,"单方造价:"]
["         审核单位:",null,null,"编制日期:","2020年03月31日"]
["         编 制 人:",null,null,"编制人证号:"]
["      审 核 人:",null,null,"审核人证号:"]
[]
["           软件名称及版本号：博奥清单计价软件V17（版本号：17.0.01）              工程计价软件测评合格编号：2016J02"]

{"sheet":"表-01_总说明","index":1,"n_rows":38,"n_cols":3,"rows_kept":38,"merged":[[0,0,0,2],[2,0,36,2]],"flags":["formulas_cached_only"]}
["总  说  明"]
["工程名称:","广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程","第1页 共1页"]
["一、工程概况：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程。\r\n\r\n二、 编制依据：\r\n\r\n\r\n   1、《建设工程工程量计算规范（GB50854～50862-2013）广西壮族自治区实施细则（修订本）》；\r\n\r\n   2、《建设工程工程量清单计价规范(GB050500-2013)广西壮族自治区实施细则》；\r\n\r\n   3、2013年版《广西壮族自治区建筑装饰装修工程消耗量定额》；\r\n\r\n   4、2013年版《广西壮族自治区建筑装饰装修工程费用定额》；\r\n\r\n   5、2016年版《广西壮族自治区建设工程费用定额》；\r\n\r\n   6、2015年版《广西壮族自治区安装工程消耗量定额》；\r\n\r\n   7、2014年《广西壮族自治区市政工程消耗量定额》及现行有关配套费率、人工和机械台班费用调整规定；\r\n\r\n   8、定额人工费及相关费率根据《自治区住房城乡建设厅关于调整建设工程定额人工费及有关费率的\r\n通知》（桂建标[2018]19号）进行调整；\r\n\r\n   9、税率根据桂造价【2019】10号文关于调整除税价计算适用增值税税率的通知；\r\n\r\n\r\n   10、材料价格主要按照《钦州市市建设工程造价信息》2020年第2期钦州港信息价计取，钦州港没有的参考钦州、南宁信息价或市场询价。\r\n\r\n\r\n   13、施工设计图纸和补充资料；"]
{"$rows_empty":34}
[null,"表-01"]

{"sheet":"表-02_建设项目预算招标汇总表","index":2,"n_rows":25,"n_cols":5,"rows_kept":25,"merged":[[0,0,0,4],[1,0,1,3],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,2,4],[3,3,4,3]],"flags":["formulas_cached_only"]}
["建设项目预算招标汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第1页 共1页"]
["序号","单项工程名称","金额(元)","其中:(元)"]
[{"$nulls":3},"暂估价","安全文明"]
[{"$nulls":4},"施工费"]
["1.1","广西中马钦州产业园区开发有限公司友谊大道中段工程1号路灯箱变10/0.4kV配电工程"]
["1.2","广西中马钦州产业园区开发有限公司友谊大道中段工程2号路灯箱变10/0.4kV配电工程"]
["1.3","广西中马钦州产业园区开发有限公司锦绣大道中段工程3号路灯箱变10/0.4kV配电工程"]
[null,"        投标报价合计"]
{"$rows_empty":15}
[{"$nulls":4},"表-02"]

{"sheet":"表-03_单项工程预算招标汇总表","index":3,"n_rows":25,"n_cols":5,"rows_kept":25,"merged":[[0,0,0,4],[1,0,1,3],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,2,4],[3,3,4,3]],"flags":["formulas_cached_only"]}
["单项工程预算招标汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第1页 共1页"]
["序号","单位工程名称","金额(元)","其中:(元)"]
[{"$nulls":3},"暂估价","安全文明"]
[{"$nulls":4},"施工费"]
["1.1.2","友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["1.1.3","友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
["1.2.1","友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["1.3.1","锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["1.3.2","锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
[null,"        投标报价合计"]
{"$rows_empty":13}
[{"$nulls":4},"表-03"]

{"sheet":"表-04_单位工程预算汇总表（分专业）","index":4,"n_rows":168,"n_cols":4,"rows_kept":168,"merged":[[0,0,0,3],[1,0,1,2],[24,0,24,3],[25,0,25,2],[48,0,48,3],[49,0,49,2],[72,0,72,3],[73,0,73,2],[96,0,96,3],[97,0,97,2],[120,0,120,3],[121,0,121,2],[144,0,144,3],[145,0,145,2]],"flags":["formulas_cached_only"]}
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第1页 共7页"]
["序号","汇总内容","金额(元)","备注"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"工程总价"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第2页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"工程总价"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第3页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"工程总价"]
["1","分部分项工程和单价措施项目清单计价合计"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第4页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第5页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["6","工程总造价"]
[null,"工程总价"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第6页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"工程总价"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
[null,"工程项目汇总"]
["1","分部分项工程和单价措施项目清单计价合计"]
["1.1","其中:暂估价"]
["2","总价措施项目清单计价合计"]
["2.1","安全文明施工费"]
[null,null," ","表-04"]
["单位工程预算汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",null,null,"第7页 共7页"]
["序号","汇总内容","金额(元)","备注"]
["3","其他项目清单计价合计"]
["4","税前项目清单计价合计"]
["5","规费、税金项目清单计价合计"]
["5.1","规费"]
["5.1","增值税"]
["6","工程总造价"]
{"$rows_empty":14}
[null,null," ","表-04"]

{"sheet":"表-08_分部分项工程和单价措施项目费用表","index":5,"n_rows":499,"n_cols":12,"rows_kept":499,"merged":[[0,0,0,11],[1,0,1,7],[1,8,1,11],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,11],[26,0,26,11],[27,0,27,7],[27,8,27,11],[28,0,29,0],[28,1,29,1],[28,2,29,2],[28,3,29,3],[28,4,29,4],[28,5,29,5],[28,6,28,11],[53,0,53,11],[54,0,54,7],[54,8,54,11],[55,0,56,0],[55,1,56,1],[55,2,56,2],[55,3,56,3],[55,4,56,4],[55,5,56,5],[55,6,55,11],[82,0,82,11],[83,0,83,7],[83,8,83,11],[84,0,85,0],[84,1,85,1],[84,2,85,2],[84,3,85,3],[84,4,85,4],[84,5,85,5],[84,6,84,11],[109,0,109,11],[110,0,110,7],[110,8,110,11],[111,0,112,0],[111,1,112,1],[111,2,112,2],[111,3,112,3],[111,4,112,4],[111,5,112,5],[111,6,111,11],[134,0,134,11],[135,0,135,7],[135,8,135,11],[136,0,137,0],[136,1,137,1],[136,2,137,2],[136,3,137,3],[136,4,137,4],[136,5,137,5],[136,6,136,11],[164,0,164,11],[165,0,165,7],[165,8,165,11],[166,0,167,0],[166,1,167,1],[166,2,167,2],[166,3,167,3],[166,4,167,4],[166,5,167,5],[166,6,166,11],[193,0,193,11],[194,0,194,7],[194,8,194,11],[195,0,196,0],[195,1,196,1],[195,2,196,2],[195,3,196,3],[195,4,196,4],[195,5,196,5],[195,6,195,11],[219,0,219,11],[220,0,220,7],[220,8,220,11],[221,0,222,0],[221,1,222,1],[221,2,222,2],[221,3,222,3],[221,4,222,4],[221,5,222,5],[221,6,221,11],[249,0,249,11],[250,0,250,7],[250,8,250,11],[251,0,252,0],[251,1,252,1],[251,2,252,2],[251,3,252,3],[251,4,252,4],[251,5,252,5],[251,6,251,11],[275,0,275,11],[276,0,276,7],[276,8,276,11],[277,0,278,0],[277,1,278,1],[277,2,278,2],[277,3,278,3],[277,4,278,4],[277,5,278,5],[277,6,277,11],[302,0,302,11],[303,0,303,7],[303,8,303,11],[304,0,305,0],[304,1,305,1],[304,2,305,2],[304,3,305,3],[304,4,305,4],[304,5,305,5],[304,6,304,11],[327,0,327,11],[328,0,328,7],[328,8,328,11],[329,0,330,0],[329,1,330,1],[329,2,330,2],[329,3,330,3],[329,4,330,4],[329,5,330,5],[329,6,329,11],[354,0,354,11],[355,0,355,7],[355,8,355,11],[356,0,357,0],[356,1,357,1],[356,2,357,2],[356,3,357,3],[356,4,357,4],[356,5,357,5],[356,6,356,11],[384,0,384,11],[385,0,385,7],[385,8,385,11],[386,0,387,0],[386,1,387,1],[386,2,387,2],[386,3,387,3],[386,4,387,4],[386,5,387,5],[386,6,386,11],[412,0,412,11],[413,0,413,7],[413,8,413,11],[414,0,415,0],[414,1,415,1],[414,2,415,2],[414,3,415,3],[414,4,415,4],[414,5,415,5],[414,6,414,11],[439,0,439,11],[440,0,440,7],[440,8,440,11],[441,0,442,0],[441,1,442,1],[441,2,442,2],[441,3,442,3],[441,4,442,4],[441,5,442,5],[441,6,441,11],[469,0,469,11],[470,0,470,7],[470,8,470,11],[471,0,472,0],[471,1,472,1],[471,2,472,2],[471,3,472,3],[471,4,472,4],[471,5,472,5],[471,6,471,11]],"flags":["formulas_cached_only"]}
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第1页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
[null,"分部分项工程"]
[null,"Ⅰ类_水电暖通消防等"]
[null,"B4 电气设备安装工程"]
["030403007001","电缆分接箱","个","1"]
[null,"6间隔，12kV高压不带开关型电缆分接箱"]
["B4-1736换","接线箱安装 明装 接线箱半周长(mm以内) 1500","个","1"]
["030414002001","送配电装置系统","系统","1"]
["B4-2082","送配电装置系统调试 10kV以下交流供电断路器","系统","1"]
["030414001001","电力变压器系统","系统","1"]
["B4-2070","电力变压器系统调试 10KV以下变压器（容量560KV.A以下）","系统","1"]
["030408001001","电力电缆  ZR-YJV22-8.7/15kV-3*120","m","800.00"]
["B4-1018换","铜芯电力电缆敷设 沿桥架垂直敷设(截面m㎡以下)120","100m","8.0000"]
["030408001002","电力电缆  ZR-YJV22-8.7/15kV-3*70","m","270.00"]
["B4-1017换","铜芯电力电缆敷设 沿桥架垂直敷设(截面m㎡以下)70","100m","2.7000"]
["030408006001","电缆终端头","个","1"]
[null,"户内冷缩终端头 NLS-3-2"]
["B4-1081换","户内冷缩式电力电缆终端头制作、安装10kV以下端头(截面m㎡以下)120","个","1"]
["030408006002","电缆终端头","个","2"]
[null,"可触摸型电缆肘型头 3*120mm2"]
["B4-1105换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)120","个","2"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第2页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["030408006003","电缆终端头","个","1"]
[null,"可触摸型电缆肘型头 3*70mm2"]
["B4-1105换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)120","个","1"]
["030408006004","电缆中间头","个","1"]
[null,"冷缩式电缆中间接头 3*120mm2（含防爆盒）"]
["B4-1145换","冷缩式电力电缆中间头制作、安装10kV以下热缩式中间头(截面m㎡以下)120","个","1"]
["030414015001","电缆试验","根","2"]
["B4-2145","绝缘子、套管、绝缘油、电缆试验  电缆试验  交流耐压试验","１０KV组/三相","2"]
["030409002001","接地母线","m","10.00"]
[null,"主变中性点及PE重复接地"]
[null,"零线接地铜线ZR-VV-70mm2"]
["B4-1203换","铜接地母线敷设 铜接地绞线敷设 截面(m㎡以内)150","10m","1.000"]
["桂030404039001","焊、压接线端子","个","8"]
[null,"铜线耳DT-70"]
["B4-0385换","焊铜接线端子 导线截面(m㎡ 以内) 70","10个","0.8"]
["030901013001","干粉灭火器4kg","具","2"]
["B9-0848换","灭火器安装 放置式","10具","0.2"]
["030414011001","接地装置","系统","1"]
["B4-2123","接地装置调试  接地网","系统","1"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第3页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"单价措施项目"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"     合    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
[null,"分部分项工程"]
[null,"市政综合工程"]
[null,"土石方工程"]
["040101003001","挖沟槽土方（机械开挖、装车）","","27.26"]
[null,"土壤类别:三类土"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第4页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"挖土深度:2米以内"]
["C1-0033换","挖掘机挖沟槽、基坑土方（斗容量1.25）装车 三类土","1000","0.02726"]
["040101003002","挖沟槽土方（机械开挖、不装车）","","19.18"]
[null,"土壤类别:三类土"]
[null,"挖土深度:2米以内"]
["C1-0029换","挖掘机挖沟槽、基坑土方（斗容量1.25）不装车 三类土","1000","0.01918"]
["040103001001","回填土","","19.18"]
[null,"密实度:按设计规范"]
[null,"填方材料品种:原土，三类土"]
[null,"填方来源、运距:原土回填"]
["C1-0101换","沟槽回填机械碾压 振动压路机1t 沟槽回填（槽底宽≤2.8m）土","100","0.1918"]
["040103001002","回填砂","","6.94"]
[null,"密实度:按设计规范"]
[null,"填方材料品种:砂"]
["C1-0099换","沟槽回填机械碾压 振动压路机1t 沟槽回填（槽底宽≤2.8m）砂","100","0.0694"]
["040103002001","余方弃置","","27.26"]
[null,"废弃料品种：三类土"]
[null,"运距：1km"]
["C1-0124换","自卸汽车运土方（运距1km内） 12t[实际3]","1000","0.02726"]
[null,"管网工程"]
["040504001001","电缆井","座","1"]
[null,"100mm厚C15商品混凝土垫层"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第5页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"井壁采用MU10红砖，M7.5水泥浆砌筑"]
[null,"井壁内抹20厚1:2.5防水水泥砂浆"]
[null,"C25商品混凝土圈梁"]
[null,"C25商品混凝土预制盖板，规格：1700*300*100"]
[null,"集水坑φ200，内填充鹅卵石"]
[null,"含模板制作、安装、拆除"]
[null,"不含挖土及钢筋"]
["C5-0671换","非定型井垫层 混凝土{换:碎石 GD40  商品普通砼  C15}","10","0.225"]
["C5-2226换","混凝土基础垫层 复合木模","10㎡","0.577"]
["C5-0673换","非定型井砌筑 砖砌 矩形{水泥砂浆中砂M7.5}","10","0.500"]
["C5-0678换","非定型井抹灰 砖墙 规格：井内侧 20mm{换:水泥防水砂浆(加防水粉5％) 1∶2.5}","100㎡","0.1863"]
["C5-0679换","非定型井抹灰 砖墙 规格：井底 20mm{换:水泥防水砂浆(加防水粉5％) 1∶2.5}","100㎡","0.0674"]
["A4-24换","混凝土 圈梁{换:碎石 GD40  商品普通砼  C25}","10","0.112"]
["A17-72换","圈梁 直形 胶合板模板 木支撑","100㎡","0.0735"]
["C5-0688换","非定型井盖板制作 盖板（板厚cm以内）10{换:碎石 GD40  商品普通砼  C25}","10","0.011"]
["C5-2241换","现浇混凝土模板 井室盖板 复合木模","10㎡","0.107"]
["C5-0747换","盖板预制 矩形盖板（板厚cm以内）10{换:碎石 GD40  商品普通砼  C25}","10","0.056"]
["C5-0693换","非定型井盖板安装 井室盖板（每块体积以内）0.1{水泥砂浆中砂M10}","10","0.056"]
["C5-2246换","预制混凝土模板 井盖板 复合木模","10㎡","0.561"]
["C3-0551换","铁件预埋 一般铁件预埋","t","0.262"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第6页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["C2-0184换","PVC管","100m","0.0340"]
["B-换","坑内回填碎石","","0.03"]
["040901001001","现浇构件钢筋","t","0.086"]
["C3-0553换","钢筋制作、安装 φ10以上","t","0.086"]
["040901001002","现浇构件钢筋","t","0.033"]
["C3-0552换","钢筋制作、安装 φ10以内","t","0.033"]
["040901002001","预制构件钢筋","t","0.276"]
["C3-0553换","钢筋制作、安装 φ10以上","t","0.276"]
["040901002002","预制构件钢筋","t","0.069"]
["C3-0552换","钢筋制作、安装 φ10以内","t","0.069"]
["040205002001","电缆保护管","m","60.00"]
["C5-1174换","塑料管安装（对接熔接）管外径（mm以内）160","10m","6.000"]
["C5-0720换","非定型管道垫层 混凝土{换:碎石 GD40  商品普通砼  C15}","10","0.085"]
["C5-2226换","混凝土基础垫层 复合木模","10㎡","0.134"]
["B-","管枕","个","36"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"单价措施项目"]
["011701","脚手架工程"]
[]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第7页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[]
[]
[]
[]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"     合    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
[null,"分部分项工程"]
[null,"Ⅰ类_水电暖通消防等"]
[null,"B4 电气设备安装工程"]
["030414002002","送配电装置系统","系统","1"]
["B4-2082","送配电装置系统调试 10kV以下交流供电断路器","系统","1"]
["030414001002","电力变压器系统","系统","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第8页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["B4-2070","电力变压器系统调试 10KV以下变压器（容量560KV.A以下）","系统","1"]
["030408001003","电力电缆  ZR-YJV22-8.7/15kV-3*70","m","382.00"]
["B4-1017换","铜芯电力电缆敷设 沿桥架垂直敷设(截面m㎡以下)70","100m","3.8200"]
["030408006005","电缆终端头","个","1"]
[null,"户内冷缩终端头 NLS-3-2"]
["B4-1081换","户内冷缩式电力电缆终端头制作、安装10kV以下端头(截面m㎡以下)120","个","1"]
["030408006006","电缆终端头","个","1"]
[null,"可触摸型电缆肘型头 3*70mm2"]
["B4-1105换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)120","个","1"]
["030414015002","电缆试验","根","1"]
["B4-2145","绝缘子、套管、绝缘油、电缆试验  电缆试验  交流耐压试验","１０KV组/三相","1"]
["030409002002","接地母线","m","10.00"]
[null,"主变中性点及PE重复接地"]
[null,"零线接地铜线ZR-VV-70mm2"]
["B4-1203换","铜接地母线敷设 铜接地绞线敷设 截面(m㎡以内)150","10m","1.000"]
["桂030404039002","焊、压接线端子","个","8"]
[null,"铜线耳DT-70"]
["B4-0385换","焊铜接线端子 导线截面(m㎡ 以内) 70","10个","0.8"]
["030901013002","干粉灭火器4kg","具","2"]
["B9-0848换","灭火器安装 放置式","10具","0.2"]
["030414011002","接地装置","系统","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第9页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["B4-2123","接地装置调试  接地网","系统","1"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"单价措施项目"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"     合    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
[null,"分部分项工程"]
[null,"Ⅰ类_水电暖通消防等"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第10页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"B4 电气设备安装工程"]
["030410002001","横担组装","组","9"]
[null,"1.名称:瓷横担绝缘子"]
[null,"2.型号:SC-210"]
["B4-1347换","10kV以下横担安装 铁横担 单根","组","9"]
["030410004001","杆上设备","组","1"]
[null,"1.名称:高压避雷器安装"]
[null,"2.型号:HY5WS"]
[null,"3.规格:17/50TLQ"]
[null,"4.电压等级(kV):10kV"]
[null,"5.支撑架种类、规格:高压避雷器担 ∠6×63×1800"]
[null,"6.含支架、横担、撑铁制安、设备安装固定、检查、调整"]
[null,"  及油开关注油、配线、接线、接地。"]
["B4-1403换","杆上变配电设备安装 避雷器{换:角钢横担∠6×63×1800、U形抱箍}","组","1"]
["B4-2001换","高压避雷器连板 —4*40*200制作安装","100kg","0.3500"]
["030410004002","杆上设备","台","1"]
[null,"1.名称:真空断路器安装、配开关牌"]
[null,"2.型号:ZW32-12F/630A"]
[null,"3.规格:630A"]
[null,"4.电压等级(kV):12kV"]
[null,"5.支撑架种类、规格:镀锌角钢横担 ∠5×50"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第11页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"6.含：支架、横担、撑铁制安、设备安装固定、检查、调整"]
["B4-1406换","杆上变配电设备安装 SF6开关{换:真空断路器安装支架}","台","1"]
["B-换","开关牌","套","1"]
["030410002002","横担组装","组","1"]
[null,"1.名称:引线担"]
[null,"2.规格:∠63×6×1700"]
["B4-1347换","10kV以下横担安装 铁横担 单根","组","1"]
["030410002003","横担组装","组","2"]
[null,"1.名称:电缆固定担"]
[null,"2.规格:∠5×50×1000"]
[null,"3.含：电缆固定担抱箍 U16×380、420、460"]
["B4-1347换","10kV以下横担安装 铁横担 单根{换:电缆固定担抱箍}","组","2"]
["030410003001","导线架设 绝缘铝绞线架设","km","0.045"]
[null,"名称：10kV绝缘导线JKLYJ-50"]
["B4-1379换","绝缘铝绞线架设 绝缘铝绞线(截面mm2以下)95{换:10kV绝缘导线JKLYJ-50}","1㎞/单线","0.045"]
["030409003001","避雷引下线","m","30.00"]
[null,"名称：铜芯线BV-50mm2，避雷器接地"]
[null,"安装形式：明敷"]
["B4-1223换","避雷引下线敷设 沿建筑、构筑物明敷引下","10m","3.000"]
["030403007002","电缆分接箱","个","1"]
[null,"6间隔，12kV高压不带开关型电缆分接箱"]
["B4-1736换","接线箱安装 明装 接线箱半周长(mm以内) 1500","个","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第12页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["030408001004","电力电缆  ZR-YJV22-8.7/15kV-3*120","m","15.00"]
["B4-1018换","铜芯电力电缆敷设 沿桥架垂直敷设(截面m㎡以下)120","100m","0.1500"]
["030408006007","电力电缆头","个","1"]
[null,"名称：高压户外冷缩式电缆头"]
[null,"型号：10KVWLN-3/2"]
["B4-1104换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)70","个","1"]
["030408006008","电缆终端头","个","2"]
[null,"可触摸型电缆肘型头 3*120mm2"]
["B4-1105换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)120","个","2"]
["030408003001","电缆保护管","m","2.50"]
[null,"镀锌角钢∠10*140*3000"]
[null,"采用2条包夹方式，配安装附件"]
[null,"敷设方式:沿电杆敷设"]
["B4-0897换","其他电缆保护管敷设 电缆保护管敷设(管径mm以下) 钢管 100-150","10m","0.250"]
["030408001005","电力电缆  ZR-YJV22-8.7/15kV-3*70","m","160.00"]
["B4-1017换","铜芯电力电缆敷设 沿桥架垂直敷设(截面m㎡以下)70","100m","1.6000"]
["030408006009","电缆终端头","个","1"]
[null,"户内冷缩终端头 NLS-3-2"]
["B4-1081换","户内冷缩式电力电缆终端头制作、安装10kV以下端头(截面m㎡以下)120","个","1"]
["030408006010","电缆终端头","个","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第13页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"可触摸型电缆肘型头 3*70mm2"]
["B4-1105换","户外电力电缆终端头制作、安装10kV以下冷缩式(截面m㎡以下)120","个","1"]
["030409001001","接地极","根","12"]
[null,"名称：镀锌地桩 ∠5×50×2500"]
["B4-1188换","接地极(板)制作、安装 角钢接地极 普通土","根","12"]
["030409002003","接地母线","m","60.00"]
[null,"名称：镀锌扁铁 —5*50*6000"]
["B4-1201换","钢接地母线敷设 户外钢接地母线敷设","10m","6.000"]
["030409002004","接地母线","m","10.00"]
[null,"主变中性点及PE重复接地"]
[null,"零线接地铜线ZR-VV-70mm2"]
["B4-1203换","铜接地母线敷设 铜接地绞线敷设 截面(m㎡以内)150","10m","1.000"]
["桂030404039003","焊、压接线端子","个","8"]
[null,"铜线耳DT-70"]
["B4-0385换","焊铜接线端子 导线截面(m㎡ 以内) 70","10个","0.8"]
["030414002003","送配电装置系统","系统","1"]
["B4-2082","送配电装置系统调试 10kV以下交流供电断路器","系统","1"]
["030414001003","电力变压器系统","系统","1"]
["B4-2070","电力变压器系统调试 10KV以下变压器（容量560KV.A以下）","系统","1"]
["030414015003","电缆试验","根","2"]
["B4-2145","绝缘子、套管、绝缘油、电缆试验  电缆试验  交流耐压试验","１０KV组/三相","2"]
["030414011003","接地装置","系统","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第14页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
["B4-2123","接地装置调试  接地网","系统","1"]
["030901013003","干粉灭火器4kg","具","2"]
["B9-0848换","灭火器安装 放置式","10具","0.2"]
[]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"单价措施项目"]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"     合    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第15页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
[null,"分部分项工程"]
[null,"市政综合工程"]
[null,"土石方工程"]
["040101003003","挖基坑土方（机械开挖、装车）","","1.15"]
[null,"土壤类别:三类土"]
[null,"挖土深度:2米以内"]
["C1-0025换","挖掘机挖沟槽、基坑土方（斗容量0.4）装车 三类土","1000","0.00115"]
["040101003004","挖基坑土方（机械开挖、不装车）","","2.06"]
[null,"土壤类别:三类土"]
[null,"挖土深度:2米以内"]
["C1-0021换","挖掘机挖沟槽、基坑土方（斗容量0.4）不装车 三类土","1000","0.00206"]
["040103001003","回填土","","2.06"]
[null,"密实度:按设计规范"]
[null,"填方材料品种:原土，三类土"]
[null,"填方来源、运距:原土回填"]
["C1-0101换","沟槽回填机械碾压 振动压路机1t 沟槽回填（槽底宽≤2.8m）土","100","0.0206"]
["040103002002","余方弃置","","1.15"]
[null,"废弃料品种：三类土"]
[null,"运距：1km"]
["C1-0124换","自卸汽车运土方（运距1km内） 12t[实际3]","1000","0.00115"]
[null,"管网工程"]
["040504001002","电缆井","座","1"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第16页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"100mm厚C15商品混凝土垫层"]
[null,"井壁采用MU10红砖，M10水泥浆砌筑"]
[null,"井壁内抹15厚1:2.5防水水泥砂浆"]
[null,"C25商品混凝土圈梁"]
[null,"集水坑φ150，内填充鹅卵石"]
[null,"含模板制作、安装、拆除"]
[null,"不含挖土及钢筋"]
["C5-0671换","非定型井垫层 混凝土{换:碎石 GD20  商品普通砼  C15}","10","0.016"]
["C5-2226换","混凝土基础垫层 复合木模","10㎡","0.051"]
["C5-0673换","非定型井砌筑 砖砌 矩形{换:水泥砂浆中砂M10}","10","0.500"]
["C5-0678换","非定型井抹灰 砖墙 规格：井内侧 20mm{换:水泥防水砂浆(加防水粉5％) 1∶2.5}","100㎡","0.0311"]
["C5-0679换","非定型井抹灰 砖墙 规格：井底 20mm{换:水泥防水砂浆(加防水粉5％) 1∶2.5}","100㎡","0.0044"]
["A4-24换","混凝土 圈梁{换:碎石 GD40  商品普通砼  C25}","10","0.014"]
["A17-72换","圈梁 直形 胶合板模板 木支撑","100㎡","0.0140"]
["C3-0551换","铁件预埋 一般铁件预埋","t","0.014"]
["C2-0184换","PVC管","100m","0.0020"]
["B-换","坑内回填碎石","","0.03"]
["040901001003","现浇构件钢筋","t","0.015"]
["C3-0553换","钢筋制作、安装 φ10以上","t","0.015"]
["040901001004","现浇构件钢筋","t","0.006"]
["C3-0552换","钢筋制作、安装 φ10以内","t","0.006"]
[]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第17页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"单价措施项目"]
["011701","脚手架工程"]
[]
[]
[]
[]
[]
[]
[null,"     小    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
[null,"     合    计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[{"$nulls":11},"表－08"]
["分部分项工程和单价措施项目费用表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"第18页 共18页"]
["定额编号","定额名称","单位","工程量","单价(元)","合价(元)","单价分析(元)"]
[{"$nulls":6},"人工费","材料费","机械费","管理费","利润","其中:\r\n暂估价"]
[null,"     ∑利  润"]
[null,"     总 合 计"]
[null,"     ∑人工费"]
[null,"     ∑材料费"]
[null,"     ∑机械费"]
[null,"     ∑管理费"]
[null,"     ∑利  润"]
{"$rows_empty":18}
[{"$nulls":11},"表－08"]

{"sheet":"表-09_总价措施费用表","index":6,"n_rows":41,"n_cols":6,"rows_kept":41,"merged":[[0,0,0,5],[1,0,1,3],[1,4,1,5],[5,2,7,2],[10,2,13,2],[16,0,16,5],[17,0,17,4],[18,0,18,5],[19,0,19,3],[19,4,19,5],[21,2,23,2],[26,2,28,2],[31,2,34,2],[39,0,39,5],[40,0,40,4]],"flags":["formulas_cached_only"]}
["总 价 措 施 费 用 表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第1页 共2页"]
["序号","项 目 名 称","计算基础","费率(%)\r\n或标准","金 额(元)","备注"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","安全文明施工费","∑分部分项及单价措施费定额(人工费+机械费)"]
["2","检验试验配合费"]
["3","雨季施工增加费"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","安全文明施工费","∑分部分项、单价措施(人工费+机械费)"]
["2","检验试验配合费"]
["3","雨季施工增加费"]
["4","工程定位复测费"]
[null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["注:以项计算的总价措施，无“计算基础”和“费率”的数值，可只填“金额”数值，但应在备注栏说明施工方案出处或计算方法。"]
[{"$nulls":5},"表-09"]
["总 价 措 施 费 用 表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第2页 共2页"]
["序号","项 目 名 称","计算基础","费率(%)\r\n或标准","金 额(元)","备注"]
["1","安全文明施工费","∑分部分项及单价措施费定额(人工费+机械费)"]
["2","检验试验配合费"]
["3","雨季施工增加费"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","安全文明施工费","∑分部分项及单价措施费定额(人工费+机械费)"]
["2","检验试验配合费"]
["3","雨季施工增加费"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","安全文明施工费","∑分部分项、单价措施(人工费+机械费)"]
["2","检验试验配合费"]
["3","雨季施工增加费"]
["4","工程定位复测费"]
[null,"         合     计"]
[]
[]
[]
["注:以项计算的总价措施，无“计算基础”和“费率”的数值，可只填“金额”数值，但应在备注栏说明施工方案出处或计算方法。"]
[{"$nulls":5},"表-09"]

{"sheet":"表-10_其他项目计价表","index":7,"n_rows":56,"n_cols":4,"rows_kept":56,"merged":[[0,0,0,3],[1,0,1,2],[26,0,26,2],[27,0,27,3],[28,0,28,2],[55,0,55,2]],"flags":["formulas_cached_only"]}
["其 他 项 目 费 用 表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程   ",null,null,"第1页 共2页"]
["序号","项目名称","计算公式","金额(元)"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["1","暂列金额","明细详见表－12－1"]
["2","材料暂估价","明细详见表－12－2"]
["3","专业工程暂估价","明细详见表－12－3"]
["4","计日工","明细详见表－12－4"]
["5","总承包服务费","明细详见表－12－5"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
["1","暂列金额","明细详见表－12－1"]
["2","材料暂估价","明细详见表－12－2"]
["3","专业工程暂估价","明细详见表－12－3"]
["4","计日工","明细详见表－12－4"]
["5","总承包服务费","明细详见表－12－5"]
[null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["1","暂列金额","明细详见表－12－1"]
["2","材料暂估价","明细详见表－12－2"]
["3","专业工程暂估价","明细详见表－12－3"]
["4","计日工","明细详见表－12－4"]
["5","总承包服务费","明细详见表－12－5"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["1","暂列金额","明细详见表－12－1"]
["2","材料暂估价","明细详见表－12－2"]
["3","专业工程暂估价","明细详见表－12－3"]
["4","计日工","明细详见表－12－4"]
["注:专业工程暂估价、检验试验费暂估价包含除税金之外的所有费用，不计规费。",null,null,"表－10"]
["其 他 项 目 费 用 表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程   ",null,null,"第2页 共2页"]
["序号","项目名称","计算公式","金额(元)"]
["5","总承包服务费","明细详见表－12－5"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
["1","暂列金额","明细详见表－12－1"]
["2","材料暂估价","明细详见表－12－2"]
["3","专业工程暂估价","明细详见表－12－3"]
["4","计日工","明细详见表－12－4"]
["5","总承包服务费","明细详见表－12－5"]
[null,"             合               计"]
{"$rows_empty":17}
["注:专业工程暂估价、检验试验费暂估价包含除税金之外的所有费用，不计规费。",null,null,"表－10"]

{"sheet":"表-12_税前项目费表","index":8,"n_rows":310,"n_cols":7,"rows_kept":310,"merged":[[0,0,0,6],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,2,6],[29,0,29,6],[31,0,31,6],[32,0,32,4],[33,0,34,0],[33,1,34,1],[33,2,34,2],[33,3,34,3],[33,4,34,4],[33,5,33,6],[60,0,60,6],[62,0,62,6],[63,0,63,4],[64,0,65,0],[64,1,65,1],[64,2,65,2],[64,3,65,3],[64,4,65,4],[64,5,64,6],[91,0,91,6],[93,0,93,6],[94,0,94,4],[95,0,96,0],[95,1,96,1],[95,2,96,2],[95,3,96,3],[95,4,96,4],[95,5,95,6],[122,0,122,6],[124,0,124,6],[125,0,125,4],[126,0,127,0],[126,1,127,1],[126,2,127,2],[126,3,127,3],[126,4,127,4],[126,5,126,6],[153,0,153,6],[155,0,155,6],[156,0,156,4],[157,0,158,0],[157,1,158,1],[157,2,158,2],[157,3,158,3],[157,4,158,4],[157,5,157,6],[184,0,184,6],[186,0,186,6],[187,0,187,4],[188,0,189,0],[188,1,189,1],[188,2,189,2],[188,3,189,3],[188,4,189,4],[188,5,188,6],[215,0,215,6],[217,0,217,6],[218,0,218,4],[219,0,220,0],[219,1,220,1],[219,2,220,2],[219,3,220,3],[219,4,220,4],[219,5,219,6],[246,0,246,6],[248,0,248,6],[249,0,249,4],[250,0,251,0],[250,1,251,1],[250,2,251,2],[250,3,251,3],[250,4,251,4],[250,5,250,6],[277,0,277,6],[279,0,279,6],[280,0,280,4],[281,0,282,0],[281,1,282,1],[281,2,282,2],[281,3,282,3],[281,4,282,4],[281,5,281,6],[308,0,308,6]],"flags":["formulas_cached_only"]}
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第1页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["1","03B001","单头螺丝1","组","1"]
[null,null,"规格型号：M16×50"]
[null,"B-换","单头螺丝M16×80","组","1"]
["2","03B002","单头螺丝2","组","1"]
[null,null,"规格型号：M16×80"]
[null,"B-换","单头螺丝M16×80","组","1"]
["3","03B003","单头螺丝3","组","4"]
[null,null,"规格型号：M16×120"]
[null,"B-换","单头螺丝M16×120","组","4"]
["4","03B004","普通抱箍","组","3"]
[null,null,"规格型号：Φ16×280、Φ16×320"]
[null,"B-换","抱箍Φ16×280、Φ16×320","组","3"]
["5","03B005","膨胀螺栓","组","6"]
[null,null,"规格型号：M10×100"]
[null,"B-换","膨胀螺栓M10×100","组","6"]
["6","03B006","电缆走向标示桩（水泥桩）","根","2"]
[null,"B-换","电缆走向标示桩（水泥桩）","根","2"]
["7","03B007","电缆走向牌(80*200mm不锈钢)","块","13"]
[null,"B-换","电缆走向牌(80*200mm不锈钢)","块","13"]
["8","050307009001","铝塑板高压柜标示牌","个","3"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压柜标示牌","块","3"]
["9","050307009002","铝塑板开关标示牌","个","2"]
[null,null,"厚度：3mm"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第2页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","铝塑板开关标示牌","块","2"]
["10","050307009003","铝塑板计量标示牌","个","4"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板计量标示牌","块","41"]
["11","050307009004","铝塑板低压总进线开关标示牌","个","2"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板低压总进线开关标示牌","块","2"]
["12","031103030001","电缆分接箱接线图","块","1"]
[null,"B-换","电缆分接箱接线图","块","1"]
["13","050307009005","铝塑板高压警示牌","个","1"]
[null,null,"“止步高压危险”"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压警示牌","块","1"]
["14","050307009006","铝塑板“设备已带电”警示牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","“设备已带电”警示牌","块","1"]
["15","050307009007","铝塑板“禁止攀登，高压危险”警示牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","“禁止攀登，高压危险”警示牌","块","1"]
["16","050307009008","铝塑板箱变标志牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板箱变标志牌","块","1"]
["17","050307009009","铝塑板电缆分接箱标志牌","个","1"]
[null,null,"“门口一带严禁停放车辆、堆放杂物等”"]
[null,null,"厚度：3mm"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第3页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","铝塑板电缆分接箱标志牌","块","1"]
["18","03B008","安全操作规程上墙600×800㎜","块","1"]
[null,"B-换","安全操作规程上墙600×800㎜","块","1"]
["19","03B009","10kV主接线图上墙 800×1200㎜","块","1"]
[null,"B-换","10kV主接线图上墙 800×1200㎜","块","1"]
["20","03B010","0.4kV主接线图上墙800×1200㎜","块","1"]
[null,"B-换","0.4kV主接线图上墙800×1200㎜","块","1"]
["21","03B011","绝缘胶垫","㎡","2.70"]
[null,null,"绝缘胶垫（长*宽*厚） 3000mm*900mm*4mm"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","㎡","2.70"]
["22","03B012","绝缘胶带","卷","5.00"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","卷","5"]
["23","03B013","绝缘手套","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘手套","双","1"]
["24","03B014","绝缘鞋","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘鞋","双","1"]
["25","03B015","验电笔","支","1"]
[null,null,"10kv"]
[null,"B-换","验电笔","支","1"]
["26","03B016","10kv接地线","根","1"]
[null,null,"3*1m+1*7m，配25平方线"]
[null,"B-换","接地线","根","1"]
["27","030408008001","防火堵洞材料","kg","40.00"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第4页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,null,"防火胶泥"]
[null,"B-换","防火胶泥","kg","40.00"]
[null,null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["28","03B017","单头螺丝1","组","1"]
[null,null,"规格型号：M16×50"]
[null,"B-换","单头螺丝M16×50","组","1"]
["29","03B018","单头螺丝2","组","1"]
[null,null,"规格型号：M16×80"]
[null,"B-换","单头螺丝M16×80","组","1"]
["30","03B019","单头螺丝3","组","4"]
[null,null,"规格型号：M16×120"]
[null,"B-换","单头螺丝M16×120","组","4"]
["31","03B020","普通抱箍","组","3"]
[null,null,"规格型号：Φ16×280、Φ16×320"]
[null,"B-换","抱箍Φ16×280、Φ16×320","组","3"]
["32","03B021","膨胀螺栓","组","6"]
[null,null,"规格型号：M10×100"]
[null,"B-换","膨胀螺栓M10×100","组","6"]
["33","03B022","电缆走向牌(80*200mm不锈钢)","块","9"]
[null,"B-换","电缆走向牌(80*200mm不锈钢)","块","9"]
["34","050307009010","铝塑板高压柜标示牌","个","3"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压柜标示牌","块","3"]
["35","050307009011","铝塑板开关标示牌","个","2"]
[null,null,"厚度：3mm"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第5页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","铝塑板开关标示牌","块","2"]
["36","050307009012","铝塑板计量标示牌","个","4"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板计量标示牌","块","4"]
["37","050307009013","铝塑板低压总进线开关标示牌","个","2"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板低压总进线开关标示牌","块","2"]
["38","050307009014","铝塑板高压警示牌","个","1"]
[null,null,"“止步高压危险”"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压警示牌","块","1"]
["39","050307009015","铝塑板“设备已带电”警示牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","“设备已带电”警示牌","块","1"]
["40","050307009016","铝塑板“禁止攀登，高压危险”警示牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","“禁止攀登，高压危险”警示牌","块","1"]
["41","050307009017","铝塑板箱变标志牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板箱变标志牌","块","1"]
["42","03B023","安全操作规程上墙600×800㎜","块","1"]
[null,"B-换","安全操作规程上墙600×800㎜","块","1"]
["43","03B024","10kV主接线图上墙 800×1200㎜","块","1"]
[null,"B-换","10kV主接线图上墙 800×1200㎜","块","1"]
["44","03B025","0.4kV主接线图上墙800×1200㎜","块","1"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第6页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","0.4kV主接线图上墙800×1200㎜","块","1"]
["45","03B026","绝缘胶垫","㎡","2.70"]
[null,null,"绝缘胶垫（长*宽*厚） 3000mm*900mm*4mm"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","㎡","2.70"]
["46","03B027","绝缘胶带","卷","5.00"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","卷","5"]
["47","03B028","绝缘手套","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘手套","双","1"]
["48","03B029","绝缘鞋","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘鞋","双","1"]
["49","03B030","验电笔","支","1"]
[null,null,"10kv"]
[null,"B-换","验电笔","支","1"]
["50","03B031","10kv接地线","根","1"]
[null,null,"3*1m+1*7m，配25平方线"]
[null,"B-换","接地线","根","1"]
["51","030408008002","防火堵洞材料","kg","30.00"]
[null,null,"防火胶泥"]
[null,"B-换","防火胶泥","kg","30.00"]
[null,null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["52","03B032","单头螺丝1","组","1"]
[null,null,"规格型号：M16×50"]
[null,"B-换","单头螺丝M16×80","组","1"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第7页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
["53","03B033","单头螺丝2","组","1"]
[null,null,"规格型号：M16×80"]
[null,"B-换","单头螺丝M16×80","组","1"]
["54","03B034","单头螺丝3","组","4"]
[null,null,"规格型号：M16×120"]
[null,"B-换","单头螺丝M16×120","组","4"]
["55","03B035","普通抱箍","组","3"]
[null,null,"规格型号：Φ16×280、Φ16×320"]
[null,"B-换","抱箍Φ16×280、Φ16×320","组","3"]
["56","03B036","膨胀螺栓","组","6"]
[null,null,"规格型号：M10×100"]
[null,"B-换","膨胀螺栓M10×100","组","6"]
["57","03B037","电缆走向牌(80*200mm不锈钢)","块","9"]
[null,"B-换","电缆走向牌(80*200mm不锈钢)","块","9"]
["58","050307009018","铝塑板高压柜标示牌","个","3"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压柜标示牌","块","3"]
["59","050307009019","铝塑板开关标示牌","个","2"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板开关标示牌","块","2"]
["60","050307009020","铝塑板计量标示牌","个","4"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板计量标示牌","块","4"]
["61","050307009021","铝塑板低压总进线开关标示牌","个","2"]
[null,null,"厚度：3mm"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第8页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","铝塑板低压总进线开关标示牌","块","2"]
["62","050307009022","铝塑板电缆分接箱标志牌","个","1"]
[null,null,"“门口一带严禁停放车辆、堆放杂物等”"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板电缆分接箱标志牌","块","1"]
["63","031103030002","电缆分接箱接线图","块","1"]
[null,"B-换","电缆分接箱接线图","块","1"]
["64","050307009023","高压开关标示牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","高压开关标示牌","块","1"]
["65","050307009024","高压刀闸牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","高压刀闸牌","块","1"]
["66","050307009025","杆号牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","杆号牌","块","1"]
["67","050307009026","铝塑板箱变标志牌","个","1"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板箱变标志牌","块","1"]
["68","050307009027","铝塑板高压警示牌","个","1"]
[null,null,"“止步高压危险”"]
[null,null,"厚度：3mm"]
[null,"B-换","铝塑板高压警示牌","块","1"]
["69","050307009028","铝塑板“设备已带电”警示牌","个","2"]
[null,null,"厚度：3mm"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第9页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
[null,"B-换","“设备已带电”警示牌","块","2"]
["70","050307009029","铝塑板“禁止攀登，高压危险”警示牌","个","2"]
[null,null,"厚度：3mm"]
[null,"B-换","“禁止攀登，高压危险”警示牌","块","2"]
["71","03B038","绝缘手套","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘手套","双","1"]
["72","03B039","绝缘鞋","双","1"]
[null,null,"10kv"]
[null,"B-换","绝缘鞋","双","1"]
["73","03B040","验电笔","支","1"]
[null,null,"10kv"]
[null,"B-换","验电笔","支","1"]
["74","03B041","10kv接地线","根","1"]
[null,null,"3*1m+1*7m，配25平方线"]
[null,"B-换","接地线","根","1"]
["75","03B042","安全操作规程上墙600×800㎜","块","1"]
[null,"B-换","安全操作规程上墙600×800㎜","块","1"]
["76","03B043","10kV主接线图上墙 800×1200㎜","块","2"]
[null,"B-换","10kV主接线图上墙 800×1200㎜","块","2"]
["77","03B044","0.4kV主接线图上墙800×1200㎜","块","5"]
[null,"B-换","0.4kV主接线图上墙800×1200㎜","块","5"]
["78","03B045","绝缘胶垫","㎡","2.70"]
[null,null,"绝缘胶垫（长*宽*厚） 3000mm*900mm*4mm"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","㎡","2.70"]
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]
["税 前 项 目 费 表"]
["工程名称：广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"第10页  共10页"]
["序号","项目编号","项目名称及项目特征描述","计量单位","工程量","金额（元）"]
[{"$nulls":5},"单价","合价"]
["79","03B046","绝缘胶带","卷","5.00"]
[null,"B-换","绝缘胶垫 1m*5m*5mm","卷","5"]
["80","030408008003","防火堵洞材料","kg","20.00"]
[null,null,"防火胶泥"]
[null,"B-换","防火胶泥","kg","20.00"]
[null,null,"                   合                 计"]
{"$rows_empty":19}
["注：税前项目包含除增值税以外的所有费用。"]
[" ",null,null," ",null,null,"表－12"]

{"sheet":"表-13_规费、税金汇总表","index":9,"n_rows":82,"n_cols":5,"rows_kept":82,"merged":[[0,0,0,4],[1,0,1,3],[6,2,13,2],[18,2,25,2],[27,0,27,4],[28,0,28,3],[34,2,41,2],[46,2,52,2],[54,0,54,4],[55,0,55,3],[62,2,69,2]],"flags":["formulas_cached_only"]}
["规费、增值税汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第1页 共3页"]
["序号","项  目  名  称","计 算 基 础","费率(%)","金额(元)"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
["1.3","工程排污费"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"友谊大道中段工程1号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
["1.3","工程排污费"]
[{"$nulls":4},"表-13"]
["规费、增值税汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第2页 共3页"]
["序号","项  目  名  称","计 算 基 础","费率(%)","金额(元)"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"友谊大道中段工程2号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
["1.3","工程排污费"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-安装部分"]
["一","给排水、燃气、电气、通风空调、消防、建筑智能、通信、自控仪表工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
[{"$nulls":4},"表-13"]
["规费、增值税汇总表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第3页 共3页"]
["序号","项  目  名  称","计 算 基 础","费率(%)","金额(元)"]
["1.3","工程排污费","∑(分部分项人工费+单价措施人工费)"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"锦绣大道中段工程3号路灯箱变10/0.4kV配电工程-市政部分"]
["一","市政综合工程(营改增)一般计税法"]
["1","规费","1.1+1.2+1.3"]
["1.1","社会保险费","∑(分部分项人工费+单价措施人工费)"]
["1.1.1","养老保险费"]
["1.1.2","失业保险费"]
["1.1.3","医疗保险费"]
["1.1.4","生育保险费"]
["1.1.5","工伤保险费"]
["1.2","住房公积金"]
["1.3","工程排污费"]
["2","增值税","Σ（分部分项工程费及单价措施项目费+总价措施项目费+其他项目费+税前项目费+规费）"]
[null,"            合              计"]
{"$rows_empty":9}
[{"$nulls":4},"表-13"]

{"sheet":"表-19_发包人提供主要材料和工程设备一览表","index":10,"n_rows":28,"n_cols":8,"rows_kept":28,"merged":[[0,0,0,7],[1,0,1,5],[1,6,1,7],[27,0,27,4]],"flags":["formulas_cached_only"]}
["发包人提供主要材料和工程设备一览表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":5},"编号："]
["序号","材料(工程设备)名称、规格、型号","单位","数量","单价(元)","交货方式","送达地点","备注"]
[1]
{"$rows_empty":23}
["注：此表由招标人填写，供投标人在投标报价、确定总承包服务费时参考。",{"$nulls":6},"表－19"]

{"sheet":"表-20_承包人提供主要材料和工程设备一览表","index":11,"n_rows":140,"n_cols":10,"rows_kept":140,"merged":[[0,0,0,9],[1,0,1,9],[2,0,2,7],[2,8,2,9],[25,0,25,9],[26,0,26,9],[28,0,28,9],[29,0,29,9],[30,0,30,7],[30,8,30,9],[53,0,53,9],[54,0,54,9],[56,0,56,9],[57,0,57,9],[58,0,58,7],[58,8,58,9],[81,0,81,9],[82,0,82,9],[84,0,84,9],[85,0,85,9],[86,0,86,7],[86,8,86,9],[109,0,109,9],[110,0,110,9],[112,0,112,9],[113,0,113,9],[114,0,114,7],[114,8,114,9],[137,0,137,9],[138,0,138,9]],"flags":["formulas_cached_only"]}
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[1,"螺纹钢筋HRB400 10以上(综合)","t",null,null,3566.92]
[2,"圆钢HPB300 Φ10以内(综合)","kg",null,null,3.64]
[3,"铁钉(综合)","kg",null,null,9.17]
[4,"电焊条（综合）","kg",null,null,5.96]
[5,"普通硅酸盐水泥 32.5MPa","t",null,null,{"v":422.3,"d":"422.30"}]
[6,"砂(综合)","",null,null,238.63]
[7,"中砂","",null,null,238.63]
[8,"国V汽油 92#","kg",null,null,7.78]
[9,"水","",null,null,3.11]
[10,"碎石 GD20  商品普通砼  C15","",null,null,{"v":383.5,"d":"383.50"}]
[11,"碎石 GD40  商品普通砼  C15","",null,null,{"v":383.5,"d":"383.50"}]
[12,"碎石 GD40  商品普通砼  C25","",null,null,412.62]
[13,"φ160*8.0mmMPP管","m",null,null,{"v":52.6,"d":"52.60"}]
[14,"干粉灭火器4kg","具",null,null,{"v":60,"d":"60.00"}]
[15,"铜芯线BV-50mm2","m",null,null,28.77]
[16,"镀锌地桩 ∠5×50×2500","根",null,null,43.19]
[17,"高压户外冷缩式电缆头10KVWLN-3/2","套",null,null,{"v":800,"d":"800.00"}]
[18,"户内冷缩终端头 NLS-3-2","套",null,null,{"v":500,"d":"500.00"}]
[19,"可触摸型电缆肘型头 3*120mm2","套",null,null,{"v":600,"d":"600.00"}]
[20,"可触摸型电缆肘型头 3*70mm2","套",null,null,{"v":560,"d":"560.00"}]
[21,"冷缩式电缆中间接头 3*120mm2（含防爆盒）","套",null,null,{"v":1804,"d":"1804.00"}]
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-20"]
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[22,"高压刀闸牌","块",null,null,{"v":45,"d":"45.00"}]
[23,"铝塑板高压柜标示牌","块",null,null,{"v":45,"d":"45.00"}]
[24,"高压开关标示牌","块",null,null,{"v":45,"d":"45.00"}]
[25,"铝塑板低压总进线开关标示牌","块",null,null,{"v":45,"d":"45.00"}]
[26,"铝塑板高压警示牌","块",null,null,{"v":45,"d":"45.00"}]
[27,"铝塑板高压柜标示牌","块",null,null,{"v":45,"d":"45.00"}]
[28,"铝塑板高压配电室门牌","块",null,null,{"v":45,"d":"45.00"}]
[29,"铝塑板计量标示牌","块",null,null,{"v":45,"d":"45.00"}]
[30,"铝塑板高压警示牌","块",null,null,{"v":45,"d":"45.00"}]
[31,"铝塑板开关标示牌","块",null,null,{"v":45,"d":"45.00"}]
[32,"铝塑板高压配电室门牌","块",null,null,{"v":45,"d":"45.00"}]
[33,"膨胀螺栓M10×100","组",null,null,{"v":9,"d":"9.00"}]
[34,"铝塑板计量标示牌","块",null,null,{"v":45,"d":"45.00"}]
[35,"验电笔","支",null,null,{"v":90,"d":"90.00"}]
[36,"10kv接地线","根",null,null,{"v":180,"d":"180.00"}]
[37,"铝塑板开关标示牌","块",null,null,{"v":45,"d":"45.00"}]
[38,"膨胀螺栓M10×100","组",null,null,{"v":9,"d":"9.00"}]
[39,"电缆走向标示桩(水泥桩）","根",null,null,{"v":75,"d":"75.00"}]
[40,"电缆走向牌","块",null,null,{"v":15,"d":"15.00"}]
[41,"U型抱箍Φ16×280、Φ16×320","组",null,null,{"v":18,"d":"18.00"}]
[42,"验电笔","支",null,null,{"v":90,"d":"90.00"}]
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-20"]
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[43,"10kv接地线","根",null,null,{"v":180,"d":"180.00"}]
[44,"安全操作规程上墙600×800㎜","块",null,null,{"v":400,"d":"400.00"}]
[45,"单头螺丝M16×120","组",null,null,{"v":9,"d":"9.00"}]
[46,"U型抱箍Φ16×280、Φ16×320","组",null,null,{"v":18,"d":"18.00"}]
[47,"单头螺丝M16×50","组",null,null,{"v":9,"d":"9.00"}]
[48,"安全操作规程上墙600×800㎜","块",null,null,{"v":400,"d":"400.00"}]
[49,"单头螺丝M16×80","组",null,null,{"v":9,"d":"9.00"}]
[50,"单头螺丝M16×120","组",null,null,{"v":9,"d":"9.00"}]
[51,"电缆分接箱接线图","块",null,null,{"v":150,"d":"150.00"}]
[52,"单头螺丝M16×50","组",null,null,{"v":9,"d":"9.00"}]
[53,"单头螺丝M16×80","组",null,null,{"v":9,"d":"9.00"}]
[54,"电缆分接箱接线图","块",null,null,{"v":150,"d":"150.00"}]
[55,"开关牌","套",null,null,{"v":105,"d":"105.00"}]
[56,"电缆走向牌","块",null,null,{"v":15,"d":"15.00"}]
[57,"防火胶泥","kg",null,null,{"v":10,"d":"10.00"}]
[58,"防火胶泥","kg",null,null,{"v":10,"d":"10.00"}]
[59,"绝缘胶带","卷",null,null,{"v":5,"d":"5.00"}]
[60,"绝缘胶带","卷",null,null,{"v":5,"d":"5.00"}]
[61,"绝缘胶垫 1m*5m*5mm","卷",null,null,{"v":350,"d":"350.00"}]
[62,"绝缘胶垫 1m*5m*5mm","卷",null,null,{"v":350,"d":"350.00"}]
[63,"绝缘手套","双",null,null,{"v":85,"d":"85.00"}]
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-20"]
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[64,"10kV绝缘导线JKLYJ-50","km",null,null,6022.56]
[65,"绝缘手套","双",null,null,{"v":85,"d":"85.00"}]
[66,"绝缘鞋","双",null,null,{"v":88,"d":"88.00"}]
[67,"铝塑板标志牌","块",null,null,{"v":45,"d":"45.00"}]
[68,"杆号牌","块",null,null,{"v":45,"d":"45.00"}]
[69,"铝塑板低压总进线开关标示牌","块",null,null,{"v":45,"d":"45.00"}]
[70,"镀锌角钢∠10*140","10m",null,null,75.72]
[71,"10kV以下横担安装 铁横担 单根","组",null,null,{"v":450,"d":"450.00"}]
[72,"电缆固定担∠5×50×1000","组",null,null,{"v":80,"d":"80.00"}]
[73,"引线担∠63×6×1700","组",null,null,{"v":140,"d":"140.00"}]
[74,"高压避雷器 HY5WS-17/5017/50TLQ","组",null,null,{"v":500,"d":"500.00"}]
[75,"高压避雷器连板 —4*40*200","kg",null,null,8.17]
[76,"真空断路器安装支架∠50×5","kg",null,null,6.15]
[77,"零线接地铜线ZR-VV-70mm2","m",null,null,40.68]
[78,"接地母线","m",null,null,7.29]
[79,"电力电缆  ZR-YJV22-8.7/15kV-3*70","m",null,null,{"v":175.6,"d":"175.60"}]
[80,"电力电缆ZR-YJV22-8.7/15kV-3*120","m",null,null,{"v":256,"d":"256.00"}]
[81,"钳接管 QLG-50","只",null,null,16.04]
[82,"电缆分接箱","个",null,null,{"v":8100,"d":"8100.00"}]
[83,"并沟线夹JB-2","只",null,null,{"v":21.5,"d":"21.50"}]
[84,"杆上变配电设备安装 SF6开关","台",null,null,{"v":18900,"d":"18900.00"}]
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-20"]
["承包人提供主要材料和工程设备一览表"]
["(适用于造价信息差额调整法)"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":7},"编号:"]
["序号","名称、规格、型号","单位","数量","风险系数(%)","基准单价(元)","投标单价(元)","确认单价(元)","价差(元)","合计差价(元)"]
[85,"汽油 93#","kg",null,null,7.78]
[86,"国V汽油 92#","kg",null,null,7.78]
[87,"轻柴油 0#","kg",null,null,6.47]
[88,"电","kW.h",null,null,0.64]
[89,"            合       计"]
{"$rows_empty":16}
["注:1.此表由招标人填写除“投标单价”栏的内容，投标人在投标时自主确定投标单价。"]
["   2.招标人应优先采用工程造价管理机构发布的单价作为基础单价，未发布的，通过市场调查确定其基准单价。"]
[{"$nulls":9},"表-20"]

{"sheet":"主要材料价格表(打勾部分)","index":12,"n_rows":103,"n_cols":6,"rows_kept":103,"merged":[[0,0,0,5],[1,0,1,2],[1,4,1,5],[31,0,31,5],[32,0,32,2],[32,4,32,5],[62,0,62,5],[63,0,63,2],[63,4,63,5],[93,0,93,5],[94,0,94,2],[94,4,94,5]],"flags":["formulas_cached_only"]}
["主要材料及价格表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第1页  共4页"]
["序号","材料编码","项目名称及规格、型号等特殊要求","单位","数量","单价（元）"]
[1,"010103002","螺纹钢筋HRB400 10以上(综合)","t"]
[2,"010903001","圆钢HPB300 Φ10以内(综合)","kg"]
[3,"030183001","铁钉(综合)","kg"]
[4,"031311001","电焊条（综合）","kg"]
[5,"040102001","普通硅酸盐水泥 32.5MPa","t"]
[6,"040301001","砂(综合)",""]
[7,"040301004","中砂",""]
[8,"140301004","国V汽油 92#","kg"]
[9,"341101001","水",""]
[10,"043103002","碎石 GD20  商品普通砼  C15",""]
[11,"043104002","碎石 GD40  商品普通砼  C15",""]
[12,"043104004","碎石 GD40  商品普通砼  C25",""]
[13,"172500000","φ160*8.0mmMPP管","m"]
[14,"230100000","干粉灭火器4kg","具"]
[15,"270508000","铜芯线BV-50mm2","m"]
[16,"270606000","镀锌地桩 ∠5×50×2500","根"]
[17,"290702100.1","高压户外冷缩式电缆头10KVWLN-3/2","套"]
[18,"290702100.2","户内冷缩终端头 NLS-3-2","套"]
[19,"290702100.2","可触摸型电缆肘型头 3*120mm2","套"]
[20,"290702100.3","可触摸型电缆肘型头 3*70mm2","套"]
[21,"290703100","冷缩式电缆中间接头 3*120mm2（含防爆盒）","套"]
[22,"B-.10","高压刀闸牌","块"]
[23,"B-.10","铝塑板高压柜标示牌","块"]
[24,"B-.11","高压开关标示牌","块"]
[25,"B-.12","铝塑板低压总进线开关标示牌","块"]
[26,"B-.12","铝塑板高压警示牌","块"]
[27,"B-.13","铝塑板高压柜标示牌","块"]
[]
["主要材料及价格表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第2页  共4页"]
["序号","材料编码","项目名称及规格、型号等特殊要求","单位","数量","单价（元）"]
[28,"B-.13","铝塑板高压配电室门牌","块"]
[29,"B-.14","铝塑板计量标示牌","块"]
[30,"B-.15","铝塑板高压警示牌","块"]
[31,"B-.15","铝塑板开关标示牌","块"]
[32,"B-.16","铝塑板高压配电室门牌","块"]
[33,"B-.16","膨胀螺栓M10×100","组"]
[34,"B-.17","铝塑板计量标示牌","块"]
[35,"B-.17","验电笔","支"]
[36,"B-.18","10kv接地线","根"]
[37,"B-.18","铝塑板开关标示牌","块"]
[38,"B-.19","膨胀螺栓M10×100","组"]
[39,"B-.1","电缆走向标示桩(水泥桩）","根"]
[40,"B-.1","电缆走向牌","块"]
[41,"B-.20","U型抱箍Φ16×280、Φ16×320","组"]
[42,"B-.20","验电笔","支"]
[43,"B-.21","10kv接地线","根"]
[44,"B-.21","安全操作规程上墙600×800㎜","块"]
[45,"B-.22","单头螺丝M16×120","组"]
[46,"B-.23","U型抱箍Φ16×280、Φ16×320","组"]
[47,"B-.23","单头螺丝M16×50","组"]
[48,"B-.24","安全操作规程上墙600×800㎜","块"]
[49,"B-.24","单头螺丝M16×80","组"]
[50,"B-.25","单头螺丝M16×120","组"]
[51,"B-.25","电缆分接箱接线图","块"]
[52,"B-.26","单头螺丝M16×50","组"]
[53,"B-.27","单头螺丝M16×80","组"]
[54,"B-.28","电缆分接箱接线图","块"]
[]
["主要材料及价格表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第3页  共4页"]
["序号","材料编码","项目名称及规格、型号等特殊要求","单位","数量","单价（元）"]
[55,"B-.29","开关牌","套"]
[56,"B-.2","电缆走向牌","块"]
[57,"B-.2","防火胶泥","kg"]
[58,"B-.3","防火胶泥","kg"]
[59,"B-.3","绝缘胶带","卷"]
[60,"B-.4","绝缘胶带","卷"]
[61,"B-.4","绝缘胶垫 1m*5m*5mm","卷"]
[62,"B-.5","绝缘胶垫 1m*5m*5mm","卷"]
[63,"B-.5","绝缘手套","双"]
[64,"B-.6","10kV绝缘导线JKLYJ-50","km"]
[65,"B-.6","绝缘手套","双"]
[66,"B-.7","绝缘鞋","双"]
[67,"B-.8","铝塑板标志牌","块"]
[68,"B-.9","杆号牌","块"]
[69,"B-.9","铝塑板低压总进线开关标示牌","块"]
[70,"B4-0897","镀锌角钢∠10*140","10m"]
[71,"B4-1347.1","10kV以下横担安装 铁横担 单根","组"]
[72,"B4-1347.2","电缆固定担∠5×50×1000","组"]
[73,"B4-1347.3","引线担∠63×6×1700","组"]
[74,"B4-1403","高压避雷器 HY5WS-17/5017/50TLQ","组"]
[75,"Z010000103.1","高压避雷器连板 —4*40*200","kg"]
[76,"Z010000103.2","真空断路器安装支架∠50×5","kg"]
[77,"Z270603001.1","零线接地铜线ZR-VV-70mm2","m"]
[78,"Z270603001.2","接地母线","m"]
[79,"Z281100000.1","电力电缆  ZR-YJV22-8.7/15kV-3*70","m"]
[80,"Z281100000.2","电力电缆ZR-YJV22-8.7/15kV-3*120","m"]
[81,"Z290626006","钳接管 QLG-50","只"]
[]
["主要材料及价格表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":3},"第4页  共4页"]
["序号","材料编码","项目名称及规格、型号等特殊要求","单位","数量","单价（元）"]
[82,"Z291115001","电缆分接箱","个"]
[83,"Z291701002","并沟线夹JB-2","只"]
[84,"B4-1406","杆上变配电设备安装 SF6开关","台"]
[85,"140301001","汽油 93#","kg"]
[86,"140301004","国V汽油 92#","kg"]
[87,"140304001","轻柴油 0#","kg"]
[88,"341103001","电","kW.h"]

{"sheet":"设备及价格表","index":13,"n_rows":4,"n_cols":7,"rows_kept":4,"merged":[[0,0,0,6],[1,0,1,4],[1,5,1,6]],"flags":["formulas_cached_only"]}
["设备及价格表"]
["工程名称:广西中马钦州产业园区友谊大道中段及锦绣大道中段工程1#、2#、3#路灯箱变工程",{"$nulls":4},"第1页  共1页"]
["序号","编码","设备名称、规格、型号等特殊要求","单位","数量","单价(元)","合价(元)"]
[1,"B4-1406","杆上变配电设备安装 SF6开关","台"]